## Runbook
Planned Outage RunBook
Site ID | Site Name | Region | Outage Description | Date | Local Start time | Local End time
LOM | LOMMEL | Europe | LOMMEL ( RITM0058244. ) | 2020-07-18 | 07:00:00 (CET) | 16:00:00 (CET)
Before Planned Outage
Sl.No | Local time | CET Time | Task | Status | Owner | Comments
1 | 15th-17th July 2020 | 12:00 PM CET | Note: Backup of the Servers will be completed before one day of maintenance activity. |  | Backup Team(Anguganesh) | Backups Will be done for all servers available in backup starting from 15th July to 17th July This will help incase any backups missed or failed to be rerun before activity start
2 | 18/07/2020 | 06:00:00 (CET) | Monitoring team to suppress alerts during Maintainance window |  | Monitoring team(sibelco-tools@wipro.com)
3 |  |  | Inform GTT about the outage -WAN Connection |  | SIAM Team
4 | 18/07/2020 |  | Inform VOIP team about the outage -VOICE Connection
5 | 18/07/2020 | 06:05:00(CET) | Power OFF the Server BE-LOM-APS-001 |  | Wintel Team(Sandiya) | OS Supported by Wintel
6 | 18/07/2020 | 06:05:00(CET) | Power OFF the Server BE-LOM-WBS-001 |  | Wintel Team(Sandiya) | OS Supported by Wintel
7 | 18/07/2020 | 06:05:00(CET) | Power OFF the Server BE-LOM-APS-101 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
8 | 18/07/2020 | 06:05:00(CET) | Power OFF the Server BE-LOM-DSK-900 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
9 | 18/07/2020 | 06:05:00(CET) | Power OFF the Server BE-LOM-PLT-003 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
10 | 18/07/2020 | 06:10:00(CET) | Power OFF the Server MHL_PRIM_DC |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
11 | 18/07/2020 | 06:10:00(CET) | Power OFF the Server MHLPC1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
12 | 18/07/2020 | 06:10:00(CET) | Power OFF the Server MHLPC2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
13 | 18/07/2020 | 06:10:00(CET) | Power OFF the Server MHLPC3 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
14 | 18/07/2020 | 06:15:00(CET) | Power OFF the Server MHLPCENG1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
15 | 18/07/2020 | 06:15:00(CET) | Power OFF the Server MHLSRVAC400CS1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
16 | 18/07/2020 | 06:15:00(CET) | Power OFF the Server MHLSRVAC400CS2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
17 | 18/07/2020 | 06:15:00(CET) | Power OFF the Server MHLSRVAC800AS1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
18 | 18/07/2020 | 06:15:00(CET) | Power OFF the Server MHLSRVAC800AS2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
19 | 18/07/2020 | 06:15:00(CET) | Power OFF the Server MHLSRVAC800CS1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
20 | 18/07/2020 | 06:20:00(CET) | Power OFF the Server MHLSRVAC800CS2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
21 | 18/07/2020 | 06:20:00(CET) | Power OFF the Server MHLSRVSMARTC |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
22 | 18/07/2020 | 06:20:00(CET) | Power OFF the ESXi Server be-lom-esx-010.sibelco-europe.amorg.group |  | Wintel Team(Sandiya) | OS Supported by Wintel
23 | 18/07/2020 | 06:20:00(CET) | Power OFF the ESXi Server be-lom-esx-011.sibelco-europe.amorg.group |  | Wintel Team(Sandiya) | OS Supported by Wintel
24 | 18/07/2020 | 06:20:00(CET) | Power 0FF the storage device -BE-LOM-SAN-001 (V3700), BE-LOM-NAS-001 (Synology) |  | Storage Team(Mohan/Manoj)
25 | 18/07/2020 |  | Network device can be powered off by onsite team |  | Onsite team
26 | 18/07/2020
27 | 18/07/2020
28 | 18/07/2020 | 06:40:00 (CET) | Power off PLC's ( IF ANY PLC DEVICE) ?????????
During Planned Outage
Sl.No | Local time | CET Time | Task | Status | Owner | Comments
After Planned Outage
Sl.No | Local time | CET Time | Task | Status | Owner | Comments
1 |  |  | Power ON PLC's ( IF ANY PLC DEVICE) ?????????and cabinet with main switch and check the all is Oaky |  | onsite resource
2 |  |  | Post power up, Network team to validate status of Network devices |  | Network team(Shankar/Manoj)
3 | 18/07/2020 |  | Onsite engineer to press the physical power button Storage devcie BE-LOM-SAN-001 (V3700), BE-LOM-NAS-001 (Synology) |  | onsite resource | Push physical button, Timo will send an email to Wipro when ready
4 | 18/07/2020 |  | Check Status of Storage Device whether it is powered up |  | Storage Team(Mohan/Manoj)
5 | 18/07/2020 |  | Check if backup server is up and able to run a test backup |  | Backup Team (Angu\Hari)
6 | 18/07/2020 | Wipro Will Check & Start | Power ON the ESXi Server be-lom-esx-010.sibelco-europe.amorg.group |  | onsite resource | OS Supported by Wintel
7 | 18/07/2020 | Wipro Will Check & Start | Power ON the ESXi Server be-lom-esx-011.sibelco-europe.amorg.group |  | onsite resource | OS Supported by Wintel
8 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server BE-LOM-APS-001 |  | Wintel Team(Sandiya) | OS Supported by Wintel
9 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server BE-LOM-WBS-001 |  | Wintel Team(Sandiya) | OS Supported by Wintel
10 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server BE-LOM-APS-101 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
11 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server BE-LOM-DSK-900 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
12 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server BE-LOM-PLT-003 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
13 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHL_PRIM_DC |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
14 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLPC1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
15 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLPC2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
16 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLPC3 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
17 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLPCENG1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
18 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLSRVAC400CS1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
19 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLSRVAC400CS2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
20 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLSRVAC800AS1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
21 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLSRVAC800AS2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
22 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLSRVAC800CS1 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
23 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLSRVAC800CS2 |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
24 | 18/07/2020 | Wipro Will Check & Start | Power ON the Server MHLSRVSMARTC |  | Wintel Team(Sandiya) | OS Not Supported by Wintel
25 |  |  | log on end- users - control systems -PLC ( IF ANY PLC DEVICE)
26 |  |  | check if other systems are up and running
27 |  |  | Site contact should send an email all are working fine.
`
additional contact for IT related check's on ABB PLC control system and MES shut-down and start-up Tonny Lemmens +32 494 500 437

## Device List(Wipro)
Network (LAN /WAN)
Site Code | Device name | Device IP | Product | Serial Number | Device Model | Comments
LOM | BE-LOM-SWS-009 | 10.32.14.16 | Cisco | FOC1331Z1EM | IE-3000-4TC
LOM | BE-LOM-SWS-010 | 10.32.14.17 | Cisco | FOC1636V1CH | IE-3000-8TC
LOM | BE-LOM-SWS-016 | 10.32.14.18 | Cisco | FOC1851Z6M7 | IE-3000-8TC
LOM | BE-LOM-SWS-001 (Stack-1) | 10.32.14.19 | Cisco | FOC1629W39W | WS-C2960S-24PS-L
LOM | BE-LOM-SWS-001 (Stack-2) | 10.32.14.19 | Cisco | FOC1629W35M | WS-C2960S-24PS-L
LOM | BE-LOM-SWS-018 | 10.32.14.20 | Cisco | FOC1737W13S | WS-C2960S-24PD-L
LOM | BE-LOM-SWS-019 | 10.32.14.21 | Cisco | FOC1705Y2N4 | WS-C2960S-24TS-L
LOM | BE-LOM-SWS-013 | 10.32.14.23 | Cisco | FOC1626Z1HN | IE-3000-8TC
LOM | BE-LOM-SWS-002 | 10.32.14.24 | Cisco | FCQ1637Y0CJ | WS-C2960-48PST-L
LOM | BE-LOM-SWS-006 | 10.32.14.26 | Cisco | FOC1713Z32Z | IE-3000-8TC
LOM | BE-LOM-SWS-017 | 10.32.14.28 | Cisco | FOC1910Y2ZT | IE-3000-8TC
LOM | BE-LOM-SWS-012 | 10.32.14.4 | Cisco | FOC1625Y3W4 | IE-3000-8TC
LOM | BE-LOM-SWS-014 | 10.32.14.5 | Cisco | FOC1243U106 | WS-C2960-8TC-L
LOM | BE-LOM-SWS-005 | 10.32.14.6 | Cisco | FOC1851Y321 | IE-3000-8TC
LOM | BE-LOM-ACP-001 | 10.32.64.152 | Cisco | FCW1909N2ZL | AIR-CAP2702I-E-K9
LOM | BE-LOM-ACP-002 | 10.32.64.164 | Cisco | FCW2026NE9W | AIR-CAP2702I-E-K9
LOM | BE-LOM-ACP-003 | 10.32.64.198 | Cisco | FCW2026NDY3 | AIR-CAP2702I-E-K9
LOM | BE-LOM-ACP-004 | 10.32.64.192 | Cisco | FCW2026NEB2 | AIR-CAP2702I-E-K9
LOM | BE-LOM-ACP-005 | 10.32.64.189 | Cisco | FCW2026NCX0 | AIR-CAP2702I-E-K9
LOM | BE-LOM-ACP-006 | 10.32.64.206 | Cisco | FCW2332PPM6 | AIR-AP2802I-E-K9
VMs Supported by Wintel
Site Code | Server Name | IP Address | OS | Server Type | vCenter
LOM | be-lom-esx-010.sibelco-europe.amorg.group | 10.32.64.228 | ESXi | Physical | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | be-lom-esx-011.sibelco-europe.amorg.group | 10.32.64.229 | ESXi | Physical | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | BE-LOM-APS-001 | 10.32.14.51 | Windows Server 2012 R2 Standard | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | BE-LOM-WBS-001 | 10.32.14.92 | Windows Server 2008 R2 Standard | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM
VMs Not Supported by Wintel
Site Code | Server Name | IP Address | OS | Server Type | vCenter
LOM | BE-LOM-APS-101 | 10.32.64.18 | Microsoft Windows 8 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | BE-LOM-DSK-900 |  | Microsoft Windows 8 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | BE-LOM-PLT-003 | 10.32.14.245 | Microsoft Windows 7 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHL_PRIM_DC | 10.32.26.5 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLPC1 | 10.32.26.80 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLPC2 | 10.32.26.81 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLPC3 | 10.32.26.82 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLPCENG1 | 10.32.26.100 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLSRVAC400CS1 | 10.32.26.17 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLSRVAC400CS2 | 172.16.168.1 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLSRVAC800AS1 | 10.32.26.15 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLSRVAC800AS2 | 10.32.26.16 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLSRVAC800CS1 | 10.32.26.25 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLSRVAC800CS2 | 10.32.61.101 | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
LOM | MHLSRVSMARTC |  | Microsoft Windows Server 2012 (64-bit) | VM | BE-DES-APS-017.SIBELCO-EUROPE.AMORG.GROUP[https:10.32.17.17]
PLC / Ifix
Site Code | Server Name | IP Address
Other Devices
Site Code | Server Name | IP Address
LOM | BE-LOM-SAN-001 | 10.32.64.235
LOM | BE-LOM-NAS-001 | 10.32.64.25
Backup Server
BE-LOM-APS-101
Site Code | Client servers | Backup Target | IP Address
LOM | BE-LOM-APS-001 | BE-LOM-NAS-001 | 10.32.64.25
BE-LOM-APS-101
BE-LOM-DSK-900
BE-LOM-PLT-003
BE-LOM-WBS-001
MHL_PRIM_DC
MHLPC1
MHLPC2
MHLPC3
MHLPCENG1
MHLSRVAC400CS1
MHLSRVAC400CS2
MHLSRVAC800AS1
MHLSRVAC800AS2
MHLSRVAC800CS1
MHLSRVAC800CS2
MHLSRVSMARTC

## Key Stakeholders Details(Wipro
STAKEHOLDERS
Sibelco SPOCs
| Name | Email ID | Contact Number | Role
| Silvia Odekerken | silvia.odekerken@sibelco.com | +32476660293 | Service Delivery Manager Central Europe
Site Plant Manager
| Name | Email ID | Contact Number | Role
31655727526
Site SPOCs
| Name | Email ID | Contact Number | Role
| Tonny Lemmens |  | +32 494 500 437 | ( Contact for IT- RELATED CHECKS)
| Harry Stienen |  | +32 475 785 984
Wipro DC Tower SPOCs
| Name | Email ID | Contact Number | Role
| Anguraj B | anguraj.b31@wipro.com | +916366385753 | Network Admin
| Sathish Selvaraj | sathish.55@wipro.com | +916366385899 | Wintel Admin
| Vimal Sankar | vimal.sankar@wipro.com | +919513682476 | Wintel Admin
| Mohankumar Varatharajan : | mohankumar.varatharajan@wipro.com; | +919700659572 | Storage Team
| Manoj Kumar | manoj.kumar143@wipro.com | +916366385849 | Storage Team
| Network Team | Sibelco-NW-Data@wipro.com
| Storage Team | Sibelco-storage@wipro.com | +916366391687
| Anguganesh R | anguganesh.ramamoorthy@wipro.com | +916366391687 | Backup Team
| Tools team | Sibelco-Wintel@wipro.com
| Field Support SPOCs | sibelco-tools1@wipro.com
Name
|  | Email ID | Contact Number | Role
Other contact
Name
| Raj Managalgi | Email ID | Contact Number | Role
|  | Rajshekar.mangalgi@wipro.com | 31650825808 | Wipro - Service Delivery Manager